## Sheet1
Physical and Financial Progress of Development Project - 2018
Ds Division :- Akkaraipattu | [9 empty] | Name of The Programme : Gamaperaliya
No | Name of Approved Project | No of Project | Allocation Amount ( Rs.Mn) | Expenditure as at 2018.11.14 in Mn | Physical Progress as at 2018.11.15 |  |  |  |  | Financial Progerss | Impress as at 2018.10.31 in Rs.Mn | Needed Impress in Rs.Mn | Amount of Liabilities as at 2018.12.31 ( In Million )
[5 empty] | Not Estimated | Estimated | Contract Awarded | In Progress | Completed
1 | Construction of Maruthayadi Road | 1 | 1 |  |  | 1 | [5 empty] | 1
2 | Construction concrete surface to Arasayadi Road | 1 | 1 |  |  | 1 | [5 empty] | 1
3 | Aalim 1st Cross Road - Concrete | 1 | 2 |  |  | 1 | [5 empty] | 2
4 | Badur Cemetry Road - Concrete | 1 | 1.5 |  |  | 1 | [5 empty] | 1.5
5 | Drainage 1st Cross Road - Concrete | 1 | 2 |  |  | 1 | [5 empty] | 2
6 | Kathar 1st Cross Road -Gravelling | 1 | 1 |  |  | 1 | [5 empty] | 1
7 | Gravelling Construction to Sakkath Village Access Road | 1 | 0.2 |  |  | 1 | [5 empty] | 0.2
8 | Gravelling Construction to Sakkath Village Mosque East Road | 1 | 0.2 |  |  | 1 | [5 empty] | 0.2
9 | Gravelling Construction to Sakkath Village Mosque East 1st Cross Right Side Road | 1 | 0.2 |  |  | 1 | [5 empty] | 0.2
10 | Gravelling Construction to Sakkath Village Mosque WestRoad | 1 | 0.2 |  |  | 1 | [5 empty] | 0.2
11 | Gravelling Construction to Sakkath Village Mosque East 2nd Cross Right side Road | 1 | 0.2 |  |  | 1 | [5 empty] | 0.2
12 | Gravelling Construction to Sambal Theevu Internal Road | 1 | 1 |  |  | 1 | [5 empty] | 1
13 | Concrete Surface Road Construction to Madarasa 3rd Cross Road, Town Division - 02 | 1 | 1 |  |  | 1 | [5 empty] | 1
14 | Construction of Concrete Surface to Badur Cemetry North Road, | 1 | 1 |  |  | 1 | [5 empty] | 1
15 | Construction of Concrete Surface to Hijra Road | 1 | 1 |  |  | 1 | [5 empty] | 1
16 | Construction of Concrete Surface to Aboobucker SI Road | 1 | 1 |  |  | 1 | [5 empty] | 1
17 | Construction of Concrete Surface to Sub Post Office 5th Cross Road | 1 | 1 |  |  | 1 | [5 empty] | 1
18 | Construction of Concrete Surface to Drainage 5th Cross Road | 1 | 1 |  |  | 1 | [5 empty] | 1
19 | Construction of Concrete Surface to Public Ground Road | 1 | 1 |  |  | 1 | [5 empty] | 1
20 | Construction of Concrete Surface to Flood Protection 1st Cross Right Side Road,Akkaraipattu - 16 | 1 | 1 |  |  | 1 | [5 empty] | 1
21 | Construction of Concrete Surface to AL Road,Pallikudiyiruppu - 01 | 1 | 1 |  |  | 1 | [5 empty] | 1
22 | Construction of Concrete Surface to Aliyar Road,Pallikudiyiruppu - 02 | 1 | 1 |  |  | 1 | [5 empty] | 1
23 | Construction of Concrete Surface to Bilal Road,Pattiyadipitty | 1 | 1 |  |  | 1 | [5 empty] | 1
24 | Construction of Concrete Surface to Central Road,Alim Nager | 1 | 1 |  |  | 1 | [5 empty] | 1
25 | Rehabilitation of Mosque at Masjithul Al -Fathah | 1 | 0.5 |  |  |  |  | 1 |  | 10% |  | 0.5
26 | Rehabilitation of Mosque at Bathur Jummah Mosque | 1 | 0.5 |  |  |  |  | 1 |  | 15% |  | 0.5
27 | Rehabilitation of Masjithul Bilal Jummah Mosque | 1 | 0.5 |  |  | 1 | [5 empty] | 0.5
28 | Rehabilitation of Pallikudiyiruppu Grand Mosque | 1 | 0.5 |  |  |  |  | 1 |  | 5% |  | 0.5
29 | Rehabilitation of Alim Naher Jumma Mosque | 1 | 0.5 |  |  |  |  | 1 |  | 5% |  | 0.5
30 | Rehabilitation of Mosque at Nooraniya Mosque | 1 | 0.5 |  |  |  |  | 1 |  | 40% |  | 0.5
Total |  | 30 | 25.5 |  |  | 25 | 1 | 4 |  |  |  | 25.5