## ONUR
ON
Ds Division :- Akkaraipattu | [8 empty] | Name of The Programme : ONUR
No | Name of Approved Project | No of Project | Allocation Amount ( Rs.Mn) | Expenditure as at 2018.11.14 in Mn | Physical Progress as at 2018.11.14 |  |  |  |  | Financial Progerss | Impress as at 2018.10.31 in Rs.Mn | Needed Impress in Rs.Mn | Amount of Liabilities as at 2018.12.31 ( In Million )
[5 empty] | Not Estimated/Not Started | Estimated | Contract Awarded | In Progress | Completed
1 | Providing of Livelihood Support to most vulnerable (Poulry Farming) - Pallikkudiruppu - 01 | 1 | 0.5 | 0.16 |  |  |  | 1 |  | 32% |  | 0.34
2 | Providing of Livelihood Support to most vulnerable (Poulry Farming) - Alim Nager | 1 | 0.81 | 0.29 |  |  |  | 1 |  | 36% |  | 0.52
3 | Improvement of Rural Community in the War Affected Village ( Providing Fishing Livelihood Equipments | 1 | 2.7 | 0 | 1 |  |  |  |  | 0% |  | 2.7
Total |  | 3 | 4.01 | 0.45 | 1 |  |  | 2 |  |  |  | 3.56