## REESP(Infrastruture)
Strengthening Reconciliation Focused on Economic Empowerment and Social Infrastructure Development Project - 2018
Division wise Physical and Financial Progress of the Month of December(2018.12.04)
Ds Division :- Akkaraipattu
No | Name of Project | Name. of GN Divisions | Total Estimated Cost (Rs.) |  | Allocation (Rs.) | Expenditure (Rs.) | Physical Progress (c) | [9 empty] | No. of Beneficiaries | Remarks
[7 empty] | A | B |  |  |  | C | D | E | F | G
|  |  | With Vat | Without Vat |  |  |  | B1 | B2 | B3 | B4
1 | Construction of New Gate Way at Km/Ak/As-Siraj Junior School | Town Division - 04 | 900000 | 783729.61 | 900000 | - | 1 | [9 empty] | 552
Total |  |  | 900000 | 783729.61 | 900000 | - | 1 | [9 empty] | 552
| Description of Rating |  |  |  | Percentage Rang
A | Estimates are being / to be prepared and initial works started |  |  |  | (0 - 5)%
B | For Constructions : B1 - Estimates approved and Bid documents prepared B2 - Quotations/Bid Called B3 - Quotations/Bid Received B4 - Contract Awarded (25% completed) Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared |  |  |  | (6 - 25)%
C | For Constructions : Start construction work,40% completed, Other : placed order for goods |  |  |  | (26 - 40)%
D | For Constructions : 60% completed Other : Received goods /instruments as per the order |  |  |  | (41 - 60)%
E | For Constructions : 80% completed Other : Received goods /instruments as per the order |  |  |  | (61 - 80)%
F | For Constructions 99% completed Other : Completed lists of goods and beneficiaries |  |  |  | (81 - 99)%
G | For Constructions 100% Completed Other : Issued goods and instruments to identified institutions/CBOs |  |  |  | 100%